Capstone Project Report

Report 2 – Project Management Plan

– Ho Chi Minh, August 2026 –

Table of Contents

I. Record of Changes	2

II. Project Management Plan	3

1. Overview	3

1.1 Scope & Estimation	3

1.2 Project Objectives	10

1.3 Project Risks	10

2. Management Approach	11

2.1 Project Process	11

2.2 Quality Management	13

2.3 Training Plan	15

3. Project Deliverables	15

4. Responsibility Assignments	16

5. Project Communications	17

6. Configuration Management	18

6.1 Document Management	18

6.2 Source Code Management	18

6.3 Tools & Infrastructures	18

# I. Record of Changes

| Date | A* M, D | In charge | Change Description |
| --- | --- | --- | --- |
| 2026-06-12 | A | Nguyen Huu Nhat Trieu (Leader) | Created Report 2 structure, estimated WBS effort (1.1), and defined Project Objectives (1.2). |
| 2026-06-13 | A | Doan Trong Khoi (Member) | Identified Project Risks (1.3) and detailed the Software Development Process model (2.1). |
| 2026-06-14 | A | Vo Trong Nhan (Member) | Formulated Quality Management (2.2), Training Plan (2.3), and defined Project Deliverables (3). |
| 2026-06-15 | A | Tran Trong Nhan (Member) | Completed Responsibility Assignments (4), Communication Plan (5), and Configuration Management (6). |
| 2026-06-16 | M | Nguyen Huu Nhat Trieu (Leader) | Reviewed, cross-checked milestones against the schedule, finalized, and approved Report 2. |
| 2026-08-14 | M | Vo Trong Nhan (Member) | Restructured Report 2 to follow the official template: rebuilt Scope & Estimation as a phase-based WBS (437 man-days), converted Project Objectives to the quality/effort format, and aligned Management Approach, Deliverables, Responsibility Assignments, and Communications with the official Report 2 sample. |

*A - Added M - Modified D - Deleted

II. Project Management Plan

1. Overview

1.1 Scope & Estimation

The capstone project is planned for approximately 90 calendar days (about 13 weeks). The team uses a phase-based project structure with Agile/Scrum development iterations. For planning purposes, the workload is estimated at 120 person-days across four members. Using 1 person-day = 8 working hours, this corresponds to about 960 team-hours, or roughly 3.7 hours per member per working day over a 5-day working week. This is a planning assumption for an academic project in which members balance capstone work with other academic commitments. The WBS below defines the planned effort and provides a basis for schedule and progress control.

| STT | WBS Item | Complexity | Est. Effort (person-days) |
| --- | --- | --- | --- |
| 1 | Project Initialization | Medium | 5 |
| 2 | Define project scope | Simple | 1 |
| 3 | Determine project requirements and objectives | Medium | 2 |
| 4 | Research existing solutions | Simple | 1 |
| 5 | Create Project Introduction document (Report 1) | Simple | 0.5 |
| 6 | Review project with mentor | Simple | 0.5 |
| 7 | Project Planning | Medium | 5 |
| 8 | Create Project Management Plan document (Report 2) | Medium | 2 |
| 9 | Set up project management and collaboration tools | Simple | 1 |
| 10 | Schedule project meetings and sprint reviews | Simple | 1 |
| 11 | Review project plan with mentor | Simple | 1 |
| 12 | Project Execution | Complex | 100 |
| 13 | Requirement Analysis Phase | Medium | 13 |
| 14 | Analyze requirements | Medium | 5 |
| 15 | Create Software Requirement Specification | Complex | 6 |
| 16 | Review requirements with mentor and stakeholders | Simple | 2 |
| 17 | Design Phase | Medium | 12 |
| 18 | Create Software Design Document | Medium | 4 |
| 19 | Create UI/UX design prototype | Medium | 4 |
| 20 | Review software design with mentor | Simple | 1 |
| 21 | Database design | Medium | 3 |
| 22 | Implementation Phase | Complex | 53 |
| 23 | User & Role Management | Medium | 5 |
| 24 | Login, Logout, Change Password | Simple | 1 |
| 25 | Google Login | Simple | 0.5 |
| 26 | Forgot / Reset Password | Simple | 0.5 |
| 27 | User Management (CRUD, status) | Medium | 1.5 |
| 28 | Role & Permission Management | Medium | 1.5 |
| 29 | Learner Management | Medium | 7 |
| 30 | Learner CRUD | Medium | 2 |
| 31 | Search & Filter Learners | Simple | 1 |
| 32 | Learner Training History | Simple | 1 |
| 33 | Learner Status Management | Simple | 1 |
| 34 | Import / Export Learner and class-roster Data | Medium | 1 |
| 35 | Track Expiring Students | Simple | 1 |
| 36 | Course & Class Management | Medium | 7 |
| 37 | Course Management | Medium | 2 |
| 38 | Subject Management | Medium | 2 |
| 39 | Class Management | Medium | 1.5 |
| 40 | Session Management | Simple | 0.5 |
| 41 | Enrollment Management | Simple | 1 |
| 42 | Attendance Management | Medium | 6 |
| 43 | Attendance Recording | Medium | 2 |
| 44 | Confirm Session | Simple | 1 |
| 45 | Attendance Statistics | Simple | 1 |
| 46 | Attendance Import (Excel) | Medium | 1.5 |
| 47 | Attendance Evidence Capture | Simple | 0.5 |
| 48 | Assessment Management | Medium | 7 |
| 49 | Assessment Creation & Scoring | Medium | 2 |
| 50 | Pass/Fail Calculation & PassingScore Snapshot | Medium | 1.5 |
| 51 | Practical Checklist Management | Medium | 1.5 |
| 52 | Instructor Evaluation & Sign-off | Simple | 1 |
| 53 | Retake Management | Simple | 1 |
| 54 | Evidence Management | Medium | 5 |
| 55 | Upload Evidence Files | Medium | 1.5 |
| 56 | Verify / Reject Evidence | Medium | 1.5 |
| 57 | Bulk Verify Evidence | Simple | 0.5 |
| 58 | Evidence Version Control | Simple | 1 |
| 59 | Evidence Type Management | Simple | 0.5 |
| 60 | ETR Workflow | Complex | 8 |
| 61 | Auto-generate ETR & Subject Results | Medium | 1.5 |
| 62 | Submit / Verify / Return ETR | Medium | 2 |
| 63 | Approve / Complete ETR (Freeze Data) | Medium | 1.5 |
| 64 | Completion Requirements & Pre-validation | Medium | 1.5 |
| 65 | Amendment / Unlock Request | Medium | 1.5 |
| 66 | Reporting & Dashboard | Medium | 4 |
| 67 | Role-based Dashboard | Medium | 1.5 |
| 68 | Reports & Export PDF/Excel | Medium | 1.5 |
| 69 | Training Package Export | Simple | 1 |
| 70 | Audit, Logging & Certificate Tracking | Medium | 1.5 |
| 71 | Audit Log | Medium | 0.5 |
| 72 | Activity History | Simple | 0.5 |
| 73 | Certificate Validity & Grounded Status | Simple | 0.5 |
| 74 | Cross-module Integration & Automated Processes | Medium | 2.5 |
| 75 | Cross-module integration validation | Medium | 1 |
| 76 | Background processing and notification checks | Simple | 0.5 |
| 77 | Regression automation and data consistency checks | Simple | 0.5 |
| 78 | Locking and audit enforcement validation | Simple | 0.5 |
| 79 | Testing Phase | Complex | 20 |
| 80 | Prepare Software Test Documentation | Complex | 5 |
| 81 | Write and execute unit tests | Complex | 7 |
| 82 | Perform integration and system tests | Complex | 5 |
| 83 | Perform acceptance testing and defect verification | Medium | 3 |
| 84 | Deployment Phase | Medium | 2 |
| 85 | Deploy software to application/server environment | Medium | 2 |
| 86 | Project Monitoring & Controlling | Medium | 3 |
| 87 | Monitor schedule, risks, issues, and changes | Medium | 3 |
| 88 | Project Closing | Medium | 5 |
| 89 | Prepare user guides, final report, and close project | Medium | 5 |

### 1.2 Project Objectives

Quality

| STT | Testing Stage | Test Coverage | No. of Defects | % of Defects | Notes |
| --- | --- | --- | --- | --- | --- |
| 1 | Reviewing | 100% of documents | 0 | 0% | Review of all requirements, design, and code documents. |
| 2 | Unit Test | ≥ 90% code coverage | ≤ 5 major defects | ≤ 2% | Focus on individual module functionality (ETR.Application.Tests). |
| 3 | Integration Test | ≥ 80% of module integrations | ≤ 10 major defects | ≤ 4% | Testing interactions between integrated modules (Enrollment, Attendance, Assessment, ETR). |
| 4 | System Test | ≥ 70% of system functionality | ≤ 10 major defects | ≤ 5% | Ensuring overall system stability and performance. |
| 5 | Acceptance Test | 100% of critical features | ≤ 5 minor defects | ≤ 3% | Final validation against user requirements. |

- Milestone Timeliness (%): The project must be finished before 31/08/2026.

- Allocated Effort (man-days): 4 (members) * 16 (weeks) * 7 (days/week) = 448 man-days.

1.3 Project Risks

The main project risks are identified below with their potential impact, likelihood, and planned mitigation actions. Risks are reviewed during weekly project monitoring and updated when conditions change.

| STT | Risk Description | Impact | Possibility | Notes |
| --- | --- | --- | --- | --- |
| 1 | Requirements change or clarification causes rework. | High | Medium | Maintain an approved baseline; refine backlog items during sprint planning and record approved changes. |
| 2 | Incorrect or incomplete training data affects record accuracy and audit readiness. | High | Medium | Use mandatory validation, QA evidence verification, and dry-run validation for bulk imports. |
| 3 | Schedule pressure in a 90-day semester limits contingency time. | High | Medium | Prioritize MUST-have features, track weekly milestones, and reserve the final period for stabilization and acceptance testing. |
| 4 | Frontend, backend, and database integration issues delay development. | Medium | Medium | Use documented API contracts, Swagger/OpenAPI, shared data models, and early integration testing. |
| 5 | Unauthorized access or data leakage affects personal training records. | High | Low | Use JWT authentication, role-based authorization, least-privilege access, input validation, and secure password hashing. |
| 6 | Team member unavailability reduces available capacity. | Medium | Low | Share knowledge, avoid single-owner critical tasks, and reassign work when necessary. |

## 2. Management Approach

## The ETR project uses a hybrid management approach: the semester is controlled through major project phases and academic milestones, while software development is performed iteratively using short Agile/Scrum sprints. This approach provides clear deliverables and deadlines for the capstone while allowing the team to refine requirements, integrate modules, and fix defects throughout development.

### 2.1 Project Process

The software development lifecycle combines phase-based planning with Agile development iterations. Requirements and design are baselined early, then implementation, testing, and refinement proceed through short 1-2 week sprints. Each sprint has a defined goal, working increment, review, and defect-fixing activities. Critical changes are prioritized and approved before being added to the active sprint.

Key components:

Requirement Analysis:

The team defines the core requirements and project scope early enough to establish the SRS and implementation baseline. During development, detailed user stories and acceptance criteria are refined as the team receives feedback. Changes are prioritized through the backlog and do not automatically change the approved scope or deadline.

Project Design:

The team prepares the system architecture, database design, API structure, and key UI flows before major implementation. Detailed design decisions may be refined during development when required by validated requirements or technical findings, while maintaining consistency with the approved architecture.

Project Implementation (Development Iterations):

Development is organized into short 1-2 week sprints. Each sprint delivers a selected set of prioritized features, together with unit tests and integration work. Work is distributed among the four members in parallel, subject to dependencies between frontend, backend, and database tasks.

Project Testing:

Testing is performed throughout development and is also consolidated into a dedicated final testing period for system-wide regression and acceptance. Developers perform unit and integration tests during implementation, followed by system and acceptance testing against the approved requirements.

Project Deployment (Incremental Delivery):

The team maintains deployable builds during development and performs controlled deployments for integration and acceptance purposes. The final deployment milestone is completed before project closure, with the backend hosted on Azure App Service, the frontend on Vercel, and the database on Azure SQL Database.

Post-deployment Stabilization:

Within the capstone period, post-deployment work is limited to defect fixing, stabilization, documentation, and minor approved adjustments required for acceptance. New feature requests outside the agreed scope are recorded as future enhancements and are not added to the final delivery without impact assessment.

2.2 Quality Management

Quality management is integrated throughout the project. The team combines preventive practices (requirements and design reviews, coding standards, peer reviews) with verification practices (unit, integration, system, and acceptance testing). Quality gates are applied before baselining major deliverables and before final deployment.

Defect Prevention:

Code Reviews:

Peer Reviews: Pull requests and significant changes are reviewed by another team member before merge or baseline approval.

Coding Standards: The team follows agreed conventions across the ASP.NET Core and React codebases to improve consistency and maintainability.

Reviewing:

Design Reviews:

Approach: Architecture, database, API contracts, and major UI flows are reviewed before implementation and revisited when material changes are introduced.

Requirements Reviews:

Approach: Requirements are reviewed during planning and sprint review activities; approved changes are prioritized and documented before implementation.

Testing:

Unit Testing:

Approach: Developers write tests for core business logic during implementation and execute them as part of the development cycle.

Integration Testing:

Approach: Integration tests validate critical interactions among frontend, API, database, and cross-module business processes.

System Testing:

Approach: System testing is performed on integrated builds during development and expanded into a final regression cycle before acceptance, covering critical role-based workflows and end-to-end ETR processes.

Acceptance Testing:

Approach: Acceptance testing is conducted with the supervisor and designated business representatives to confirm that critical requirements and workflows are satisfied before final delivery.

Documentation:

Test Documentation:

Approach: Test strategy, cases, execution results, defect records, and acceptance evidence are maintained for the project and updated as the system evolves.

Defect Tracking:

Approach: Defects are recorded in GitHub Issues, prioritized by severity and impact, assigned to responsible members, and verified after correction.

2.3 Training Plan

| Training Area | Participants | When, Duration | Waiver Criteria |
| --- | --- | --- | --- |
| Git, GitHub | All members | week 1 | Mandatory |
| React + Vite (Frontend) | All members | week 2 - week 6 | Mandatory |
| ASP.NET Core & EF Core (Backend) | All members | week 2 - week 6 | Mandatory |
| SQL Server (Azure SQL Database) | All members | week 3 - week 5 | Mandatory |
| UI/UX Design | Nhan - SE171973 | week 1 - week 5 |  |

3. Project Deliverables

The main project deliverables, both internal and external, are listed in the table below with their planned due dates.

| STT | Deliverable | When, Duration | Waiver Criteria |
| --- | --- | --- | --- |
| 1 | Project Introduction (Report 1) | 06/2026 | Project introduction document |
| 2 | Project Management Plan (Report 2) | 06/2026 | Project management plan document |
| 3 | Software Requirement Specification (Report 3) | 07/2026 | Context diagram, use case diagram, functional requirements |
| 4 | Software Design Document (Report 4) | 07/2026 | System architecture, class diagram, sequence diagram |
| 5 | Software Test Documentation (Report 5) | 08/2026 | Test strategy, test plan, test cases |
| 6 | Software User Guides (Report 6) | 08/2026 | Installation guides, user manual guides |
| 7 | Final Project Report | 08/2026 | Include all project documents |
| 8 | Code Package Back-end | 08/2026 | ASP.NET Core source code (ETR_Record_BE) |
| 9 | Code Package Front-end | 08/2026 | React source code (ETR_FE) |
| 10 | Deployed System | 08/2026 | Azure App Service, Azure SQL Database, Vercel |

## 4. Responsibility Assignments

The responsibility assignment matrix below describes the main responsibilities of each team member for the project outputs.

D~Do; R~Review; S~Support; I~Informed; <blank>- Omitted

| Responsibility | Nguyen Huu Nhat Trieu (Leader) | Vo Trong Nhan | Doan Trong Khoi | Tran Trong Nhan |
| --- | --- | --- | --- | --- |
| Project Introduction (Report 1) | R | D | D | D |
| Project Management Plan (Report 2) | R | D | D | D |
| Software Requirement Specification (Report 3) | R | D | D | D |
| Software Design Document (Report 4) | R | D | D | D |
| Software Test Documentation (Report 5) | R | D | D | D |
| Software User Guides (Report 6) | R | D | D | D |
| Final Project Report | D | D | D | D |
| Code Package Back-end | D | I | D | I |
| Code Package Front-end | I | D | I | D |
| UI/UX design prototype | I | D | I | D |
| Database Design & Migrations | D | S | D | S |

## 5. Project Communications

| Communication Item | Description | When, Frequency | Type, Tool, Method(s) |
| --- | --- | --- | --- |
| Supervisor (Lecturer) | Provide document template; instruct the project team; review deliverables; supervise project status; receive project report | Weekly | Zalo / Google Meet |
| Weekly team meeting | All team members collaborate on mutual tasks; plan the next sprint | Weekly (during class) | Offline / Google Meet |
| Sprint review & demo | Demo completed features and collect feedback | End of each sprint | Offline / Google Meet |
| Code review | Review pull requests and ensure code quality | Per pull request | GitHub |
| Status report | Leader reports overall progress and risks to the supervisor | Weekly | Email / Google Docs |
| Messages / face-to-face meeting | Share daily progress on project tasks; share current and potential roadblocks | Daily | Zalo |

## 6. Configuration Management

### 6.1 Document Management

- Document tools: Google Docs, Microsoft Office.

- File management: Google Drive (reports and working documents); project documentation is also versioned in the GitHub repositories (docs/ folder).

### 6.2 Source Code Management

- Our team uses GitHub to manage the source code version (ETR_Record_BE and ETR_FE repositories), using Git branching and pull requests.

6.3 Tools & Infrastructures

| Category | Tools / Infrastructure |
| --- | --- |
| Technology | React + Vite (Frontend); ASP.NET Core / .NET 9 (Backend) |
| Database | SQL Server / Azure SQL Database |
| IDEs / Editors | Visual Studio Code; Antigravity, OpenAI |
| Diagramming | Draw.io |
| Documentation | Microsoft Office; Google Docs/Sheets/Slides |
| Version Control | GitHub repositories with branches and pull requests |
| Document Storage | Google Drive with controlled naming/versioning |
| Deployment | Vercel (Frontend); Azure App Service (Backend); Azure SQL Database |